## Gantt
Persons | Alex P. | Devin D. | Drew C. | Garrett O. | Luke H. | Miranda R. | Travis R. | Zach M. | Zane G. | # | Travis R.
To do 1 | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | Documentation/SA demo | 2 | Documentation/SA demo
To do 2 | Specify data structure for rooms and doors | Github setup, Etc. | Learning C#/Unity | Requirements Collection | Write Skeleton Code/Public Headers | Learn Unity | Create Inventory | Overall Design Idea | Outline Manager and Functions | 3 | Create Inventory
To do 3 | setup room generation algorithms | Write Public functions, basic structure | Parsing the data from others | Enemy Population/inventory databases | Write Acceptance Test plan | Code feature | Create test Items | Program Working Sample | Build Sound Library | 4 | Create test Items
To do 4 | get initial main path of rooms generating (from start to middle to end) | Make inert obstacles | Encoding it in some standard | Enemy Design | Write classes that will be inheritated by enemy class | Test Code | Make items stack/swap | Implement w/ Team’s Code | Working Functions for all possible audio requests | 5 | Make items stack/swap
To do 5 | get branching rooms to generate | Make Simple Interactables | Reading/Writing to disk | Enemy Generation programming | Write remaining core features | Join code with rest of teams | Integrate Inventory into the main game | All Menus Functioning | Testing/Debugging | 6 | Integrate Inventory into the main game
To do 6 | generate visuals for rooms | Make Level Exit/Dodo Egg | Parsing data from disk | Enemy behavior programming | Update Gantt Chart | Debugging | Make item objects in game move to inventory | Allow for Settings Changes | Algorithm for dynamic pitch of sounds | 7 | Make item objects in game move to inventory
To do 7 | Create physics colliders around rooms | Make Optional Obstacles | Passing data in a useful way to the others | User Documentation | Finish coding any missing features | Rejoining code with teams | Testing | Implement Final Aesthetic Designs | Modify sounds/music for optimal load times | 8 | Testing
To do 8 | Populate rooms with enemies & items | Integrate other's parts that were not previously working | Testing | Testing | Test Release Candidate Make last-minute changes | Playing game to ensure works | Create all necessary items | Testing | Testing/Debugging | 9 | Create all necessary items
To do 9 | Spawn player object in start room, and exit object in end room. | Final testing and build | Presentation | Installation | Presentation | Presentation | Final Testing | Installation/Release | Presentation | 10 | Final Testing
Start Date 1 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 11 | 2018-01-15
Start Date 2 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 12 | 2018-02-12
Start Date 3 | 2018-02-19 | 2018-02-19 | 2018-02-26 | 2018-02-19 | 2018-02-19 | 2018-02-19 | 2018-02-26 | 2018-02-19 | 2018-02-19 | 13 | 2018-02-26
Start Date 4 | 2018-03-05 | 2018-03-12 | 2018-03-12 | 2018-02-26 | 2018-02-26 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-12 | 14 | 2018-03-05
Start Date 5 | 2018-03-26 | 2018-04-02 | 2018-03-26 | 2018-03-12 | 2018-03-05 | 2018-03-19 | 2018-03-19 | 2018-03-19 | 2018-03-26 | 15 | 2018-03-19
Start Date 6 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-03-26 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-03-26 | 2018-04-02 | 16 | 2018-04-02
Start Date 7 | 2018-04-16 | 2018-04-16 | 2018-04-23 | 2018-04-09 | 2018-04-09 | 2018-04-16 | 2018-04-16 | 2018-04-02 | 2018-04-16 | 17 | 2018-04-16
Start Date 8 | 2018-04-23 | 2018-04-23 | 2018-04-30 | 2018-04-23 | 2018-04-23 | 2018-04-30 | 2018-04-23 | 2018-04-16 | 2018-04-30 | 18 | 2018-04-23
Start Date 9 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 2018-04-30 | 2018-05-03 | 2018-05-03 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 19 | 2018-04-30
Duration 1 | 28 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 20 | 28
Duration 2 | 7 | 6 | 14 | 7 | 7 | 7 | 14 | 7 | 7 | 21 | 14
Duration 3 | 14 | 6 | 14 | 7 | 7 | 14 | 7 | 14 | 21 | 22 | 7
Duration 4 | 21 | 6 | 14 | 14 | 7 | 14 | 14 | 14 | 14 | 23 | 14 | Alex
Duration 5 | 14 | 3 | 14 | 14 | 28 | 14 | 14 | 7 | 7 | 24 | 14
Duration 6 | 7 | 3 | 14 | 14 | 7 | 14 | 14 | 7 | 14 | 25 | 14
Duration 7 | 7 | 6 | 7 | 14 | 14 | 14 | 7 | 14 | 14 | 26 | 7
Duration 8 | 7 | 3 | 3 | 7 | 10 | 3 | 7 | 14 | 3 | 27 | 7
Duration 9 | 3 | 3 | 0 | 3 | 0 | 0 | 3 | 3 | 0 | 28 | 3
Completed 1 | 28 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29 | 28
Completed 2 | 7 | 18 | 14 | 7 | 7 | 7 | 14 | 7 | 7 | 30 | 14
Completed 3 | 14 | 7 | 14 | 7 | 7 | 14 | 7 | 14 | 21 | 31 | 7 | Devin
Completed 4 | 14 | 4 | 7 | 14 | 7 | 14 | 14 | 14 | 7 | 32 | 14
Completed 5 | 0 | 4 | 0 | 6 | 0 | 0 | 14 | 0 | 0 | 33 | 14
Completed 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0
Completed 7 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0
Completed 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0
Completed 9 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0
Incomplete 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | Drew
Incomplete 2 | 0 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0
Incomplete 3 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
Incomplete 4 | 7 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 41 | 0
Incomplete 5 | 14 | -1 | 14 | 8 | 28 | 14 | 0 | 7 | 7 | 42 | 0
Incomplete 6 | 7 | -3 | 14 | 14 | 7 | 14 | 14 | 7 | 14 | 43 | 14
Incomplete 7 | 7 | 2 | 7 | 14 | 14 | 14 | 7 | 14 | 14 | 44 | 7
Incomplete 8 | 7 | -4 | 3 | 7 | 10 | 3 | 7 | 14 | 3 | 45 | 7
Incomplete 9 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 3 | 0 | 46 | 3 | Garrett
| Alex | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Specify data structure for rooms and doors | 7 | 0
|  | 2018-02-19 | setup room generation algorithms | 14 | 0
|  | 2018-03-05 | get initial main path of rooms generating (from start to middle to end) | 14 | 7
|  | 2018-03-26 | get branching rooms to generate | 0 | 14 | [6 empty] | Luke
|  | 2018-04-09 | generate visuals for rooms | 0 | 7
|  | 2018-04-16 | Create physics colliders around rooms | 0 | 7
|  | 2018-04-23 | Populate rooms with enemies & items | 0 | 7
|  | 2018-04-30 | Spawn player object in start room, and exit object in end room. | 0 | 3
| Devin | 2018-01-15 | Documentation/SA demo | 24 | 0
|  | 2018-02-12 | Github setup, Etc. | 18 | -12 | [6 empty] | Miranda
|  | 2018-02-19 | Write Public functions, basic structure | 7 | -1
|  | 2018-03-12 | Make inert obstacles | 4 | 2
|  | 2018-04-02 | Make Simple Interactables | 4 | -1
|  | 2018-04-09 | Make Level Exit/Dodo Egg | 6 | -3
|  | 2018-04-16 | Make Optional Obstacles | 4 | 2
|  | 2018-04-23 | Integrate other's parts that were not previously working | 7 | -4
|  | 2018-04-30 | Final testing and build | 3 | 0 | [6 empty] | Travis
| Drew | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Github setup, Etc. | 14 | 0
|  | 2018-02-26 | Write Public functions, basic structure | 14 | 0
|  | 2018-03-12 | Make inert obstacles | 7 | 7
|  | 2018-03-26 | Make Simple Interactables | 0 | 14
|  | 2018-04-09 | Make Level Exit/Dodo Egg | 0 | 14 | [6 empty] | Zach
|  | 2018-04-23 | Make Optional Obstacles | 0 | 7
|  | 2018-04-30 | Integrate other's parts that were not previously working | 0 | 3
|  | 2018-05-03 | Final testing and build | 0 | 0
| Garrett | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Learning C#/Unity | 7 | 0
|  | 2018-02-19 | Parsing the data from others | 7 | 0 | [6 empty] | Zane
|  | 2018-02-26 | Encoding it in some standard | 14 | 0
|  | 2018-03-12 | Reading/Writing to disk | 6 | 8
|  | 2018-03-26 | Parsing data from disk | 0 | 14
|  | 2018-04-09 | Passing data in a useful way to the others | 0 | 14
|  | 2018-04-23 | Testing | 0 | 7
| Luke | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Write Skeleton Code/Public Headers | 7 | 0
|  | 2018-02-19 | Write Acceptance Test plan | 7 | 0
|  | 2018-02-26 | Write classes that will be inheritated by enemy class | 7 | 0
|  | 2018-03-05 | Write remaining core features | 0 | 28
|  | 2018-04-02 | Update Gantt Chart | 0 | 7
|  | 2018-04-09 | Finish coding any missing features | 0 | 14
|  | 2018-04-23 | Test Release Candidate Make last-minute changes | 0 | 10
| Miranda | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Learn Unity | 7 | 0
|  | 2018-02-19 | Code feature | 14 | 0
|  | 2018-03-05 | Test Code | 14 | 0
|  | 2018-03-19 | Join code with rest of teams | 0 | 14
|  | 2018-04-02 | Debugging | 0 | 14
|  | 2018-04-16 | Rejoining code with teams | 0 | 14
|  | 2018-04-30 | Playing game to ensure works | 0 | 3
| Travis | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Create Inventory | 14 | 0
|  | 2018-02-26 | Create test Items | 7 | 0
|  | 2018-03-05 | Make items stack/swap | 14 | 0
|  | 2018-03-19 | Integrate Inventory into the main game | 14 | 0
|  | 2018-04-02 | Make item objects in game move to inventory | 0 | 14
|  | 2018-04-16 | Testing | 0 | 7
|  | 2018-04-23 | Create all necessary items | 0 | 7
| Zach | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Overall Design Idea | 7 | 0
|  | 2018-02-19 | Program Working Sample | 14 | 0
|  | 2018-03-05 | Implement w/ Team’s Code | 14 | 0
|  | 2018-03-19 | All Menus Functioning | 0 | 7
|  | 2018-03-26 | Allow for Settings Changes | 0 | 7
|  | 2018-04-02 | Implement Final Aesthetic Designs | 0 | 14
|  | 2018-04-16 | Testing | 0 | 14
| Zane | 2018-01-15 | Documentation/SA demo | 28 | 0
|  | 2018-02-12 | Outline Manager and Functions | 7 | 0
|  | 2018-02-19 | Build Sound Library | 21 | 0
|  | 2018-03-12 | Working Functions for all possible audio requests | 7 | 7
|  | 2018-03-26 | Testing/Debugging | 0 | 7
|  | 2018-04-02 | Algorithm for dynamic pitch of sounds | 0 | 14
|  | 2018-04-16 | Modify sounds/music for optimal load times | 0 | 14
|  | 2018-04-30 | Testing/Debugging | 0 | 3
|  | 2018-05-03 | Presentation | 0 | 0
Note on B2: Travis Rousey: Highlighted boxes are the ones we should update if any changes.

## HoursCost
Alex P. | Estimated Hours | Actual Hours
Documentation/SA demo | 5
Specify data structure for rooms and doors | 5
setup room generation algorithms | 5
get initial main path of rooms generating (from start to middle to end) | 5
get branching rooms to generate | 5
generate visuals for rooms | 5
Create physics colliders around rooms | 5
Populate rooms with enemies & items | 5
Spawn player object in start room, and exit object in end room. | 5
Devin D.
Documentation/SA demo | 5
Write Public functions, basic structure | 5
Program core features | 5
Program optional features | 5
Debug main features | 5
Debug optional features | 5
Documentation | 5
Testing | 5
Release Build | 5
Drew C.
Documentation/SA demo | 5
Learning C#/Unity | 5
Parsing the data from others | 5
Encoding it in some standard | 5
Reading/Writing to disk | 5
Parsing data from disk | 5
Passing data in a useful way to the others | 5
Testing | 5
Presentation | 5
Garrett O.
Documentation/SA demo | 5
Requirements Collection | 5
Enemy Population/inventory databases | 5
Enemy Design | 5
Enemy Generation programming | 5
Enemy behavior programming | 5
User Documentation | 5
Testing | 5
Installation | 5
Luke H.
Documentation/SA demo | 13.5 | 16.25
Write Skeleton Code/Public Headers | 10 | 6
Write Acceptance Test plan | 7 | 7.5
Write classes that will be inheritated by enemy class | 7 | 0
Write remaining core features | 7 | 5
Update Gantt Chart | 5
Finish coding any missing features | 6
Test Release Candidate Make last-minute changes | 5
Presentation | 5
Miranda R.
Documentation/SA demo | 5
Learn Unity | 5
Code feature | 5
Test Code | 5
Join code with rest of teams | 5
Debugging | 5
Rejoining code with teams | 5
Playing game to ensure works | 5
Presentation | 5
Travis R.
Documentation/SA demo | 5 | 8
Create Inventory | 15 | 22
Create test Items | 5 | 3.25
Make items stack/swap | 5 | 13
Integrate Inventory into the main game (4/12/2018) | 5 | 6
Make item objects in game move to inventory | 5 | 0
Testing | 5 | 0
Create all necessary items | 5 | 0
Final Testing | 5 | 0
Zach M.
Documentation/SA demo | 5
Overall Design Idea | 5
Program Working Sample | 5
Implement w/ Team’s Code | 5
All Menus Functioning | 5
Allow for Settings Changes | 5
Implement Final Aesthetic Designs | 5
Testing | 5
Installation/Release | 5
Zane G.
Documentation/SA demo | 5
Outline Manager and Functions | 5
Build Sound Library | 5
Working Functions for all possible audio requests | 5
Testing/Debugging | 5
Algorithm for dynamic pitch of sounds | 5
Modify sounds/music for optimal load times | 5
Testing/Debugging | 5
Presentation | 5
| Total Estimated Hours | Total Actual Hours | Estimated Cost | Actual Cost
| 435.5 | 87 | 43550 | 8700