## Sheet1
Task | Expected | Actual | Difference
Documentation/SA demo | 24 | 24 | 0
Github setup, Etc. | 6 | 18 | -12
Write Public functions, basic structure | 6 | 7 | -1
Make inert obstacles | 6 | 4 | 2
Make Simple Interactables | 3 | 4 | -1
Make Level Exit/Dodo Egg | 3 | 6 | -3
Make Optional Obstacles | 6 | 4 | 2
Integrate other's parts that were not previously working | 3 | 7 | -4
Final testing and build | 3 | 3 | 0
Total | 60 | 77 | -17